# Strategic Planning and Needs Analysis for ERP Implementation

Project ERP Implementation Consultant  |  Week 1  |  30 October 2026

| Case basis | Planning position |
| --- | --- |
| Business | Horizon Foods Ltd. is a hypothetical mid-sized packaged-food manufacturer with two plants, three distribution centres, and finance, procurement, inventory, sales, and production teams. |
| Current-state assumption | The teams use separate spreadsheets and departmental tools. Repeated entry, inconsistent product/supplier records, delayed stock visibility, and slow month-end reconciliation are planning assumptions for this exercise, not observed company facts. |
| Recommendation | Proceed to a time-boxed discovery and fit-to-standard assessment before selecting a platform or approving full implementation funding. |

# Executive summary

This strategic plan frames an ERP implementation as a business-change programme with clear ownership, data controls, process decisions, testing, training, and post-launch support. In the hypothetical Horizon Foods scenario, separate departmental records make it difficult to answer a basic operating question consistently: which customer orders, material balances, purchase commitments, production plans, and financial postings are current? A shared ERP process and governed master data could reduce duplicate entry and improve traceability, but software alone will not resolve unclear ownership or poor data.

The proposed approach follows SAP Activate’s six-phase structure—Discover, Prepare, Explore, Realize, Deploy, and Run—as a planning reference. The schedule below is an indicative 24-week plan, not a vendor commitment or an executed project. Each phase ends with a decision gate so the sponsor can stop, adjust, or proceed based on evidence. [1][2]

# 1. Introduction and business need

Horizon Foods is modeled as a growing manufacturer whose teams maintain separate order, purchasing, warehouse, production, and finance records. The resulting risks include multiple versions of the same supplier or product, late notice of shortages, rekeyed orders, weak audit trails, and reconciliation effort at period close. The case does not claim these issues were measured in a real company; discovery interviews and sample-document reviews would be needed to validate them.

An ERP programme is justified only if a process and data assessment confirms that the business benefits exceed the implementation and change costs. The first decision is therefore not ‘which software?’ but ‘which processes, controls, data owners, and outcomes must be improved?’ A fit-to-standard review should test whether established processes meet the need before custom development is considered.

# 2. Scope and boundaries

| In scope for discovery and planning | Out of scope until approved |
| --- | --- |
| Order-to-cash, procure-to-pay, record-to-report, inventory management, and production planning across two plants and three distribution centres. | Selecting or purchasing a specific ERP product, signing a vendor contract, or committing a production go-live date. |
| Process ownership, role/access needs, master-data domains, reporting, integration inventory, migration approach, and change/training needs. | Replacing specialist systems or redesigning every business process before fit-to-standard workshops. |
| Indicative success measures, risks, governance, phased timeline, and decision gates. | Claiming live configuration, system testing, measured savings, or completed implementation work. |

# 3. Strategic workstreams and success factors

| Workstream | Critical success factor | Evidence / proposed acceptance measure |
| --- | --- | --- |
| Leadership and governance | A sponsor resolves cross-functional decisions and protects key-user time. | Named sponsor, steering group, decision log, and one accountable owner per process. |
| Process design | Fit-to-standard is used before customization; exceptions have a business reason and owner. | Signed process decisions and approved list of gaps/extensions. |
| Data readiness | Data owners define quality rules, cleansing, mapping, and reconciliation before migration. | Critical fields have owners; sample records pass agreed completeness and validity checks. |
| Testing and controls | End-to-end scenarios cover normal, exception, security, and financial reconciliation paths. | Critical tests pass; defects have severity, owner, due date, and retest evidence. |
| People and language | Role-based training and bilingual support reach affected users before cutover. | Attendance, task-based practice, comprehension checks, and a support/escalation channel. |
| Operations readiness | Support, monitoring, access, backup, cutover, and rollback decisions are explicit. | Readiness checklist approved by business, IT, and process owners. |

# 4. Indicative 24-week implementation roadmap

| Phase | Weeks | Main activities | Milestone / gate |
| --- | --- | --- | --- |
| Discover | 1–2 | Confirm business case, scope, outcomes, solution options, and key constraints. | Sponsor approves discovery findings and whether to prepare. |
| Prepare | 3–5 | Set governance, team roles, plan, environment strategy, risk log, and communication cadence. | Project charter and mobilization plan approved. |
| Explore | 6–9 | Run fit-to-standard workshops; map current/future processes; define data, integration, security, and reporting needs. | Design decisions and prioritized gaps signed off. |
| Realize | 10–17 | Configure in iterations; cleanse and map sample data; build integrations; test process scenarios and train super-users. | End-to-end test exit criteria met; critical defects closed or accepted. |
| Deploy | 18–21 | Rehearse cutover, complete role-based training, verify data reconciliation, obtain readiness approvals, and move to production only after go/no-go. | Go/no-go decision and business-owner sign-off. |
| Run | 22–24 | Provide hypercare, triage issues, monitor service and data quality, transfer ownership to support, and review lessons. | Support handover and first post-launch review completed. |

The phase order reflects SAP Activate guidance; durations, activities, and decision gates above are tailored planning assumptions for this hypothetical case and must be re-estimated after scope, product, deployment model, and resource availability are known.

# 5. Roles and decision ownership

| Role | Core responsibility |
| --- | --- |
| Executive sponsor | Owns business case, funding gate, priority conflicts, and go/no-go decision. |
| Project manager | Maintains integrated plan, dependencies, risks, decisions, and status reporting. |
| Process owners / key users | Approve process design, data definitions, test scenarios, training content, and readiness. |
| ERP functional and technical leads | Translate approved requirements into solution design; manage configuration, integration, security, and technical quality. |
| Data owners / migration lead | Profile, cleanse, map, load, reconcile, and obtain business approval for data. |
| Change and language lead | Assess role impacts, prepare bilingual communications, coordinate training, and collect feedback. |

# 6. Risk assessment

| Risk | Likelihood / impact | Mitigation and early warning | Owner |
| --- | --- | --- | --- |
| Uncontrolled scope growth | Medium / High | Baseline process scope; route changes through impact review; track unapproved requests. | Sponsor + PM |
| Poor or duplicated master data | High / High | Assign data owners; profile sample records early; define duplicate, mandatory-field, and reconciliation rules. | Data lead |
| Excess customization | Medium / High | Demonstrate standard process first; require business case and upgrade/support impact for each extension. | Process owners |
| Language misunderstanding | Medium / High | Use bilingual glossary, plain-language scripts, reviewed translations, and teach-back for critical instructions. | Change lead |
| Low user adoption / key-user overload | Medium / High | Protect user time; train by role; monitor attendance and practice completion; provide floor support. | Business leads |
| Integration or cutover failure | Medium / High | Rehearse realistic end-to-end flows; reconcile totals; set go/no-go thresholds and rollback ownership. | IT lead + PM |
| Access or sensitive-data exposure | Low–Medium / High | Define least-privilege roles; review segregation of duties; test access and incident response before launch. | Security lead |

# 7. Communication strategy with Mandarin HSK 4 support

Use short, role-based updates with one decision or action per message. Publish English and simplified-Chinese versions side by side for key-user workshops, training, cutover steps, and urgent notices. Keep ERP product names, module names, transaction IDs, and field identifiers unchanged, then add a plain Chinese explanation and an English gloss. A bilingual reviewer should check meaning, tone, and local business usage; machine translation alone is not sufficient for financial, access, or cutover instructions.

| HSK 4 vocabulary (HSK 3.0 examples) | Pinyin | Meaning | Use in ERP communication |
| --- | --- | --- | --- |
| 计划 | jìhuà | plan | 本周计划 / This week’s plan |
| 任务 | rènwu | task | 分配任务 / Assign a task |
| 安排 | ānpái | arrangement; schedule | 培训安排 / Training schedule |
| 按时 | ànshí | on time | 请按时完成 / Please complete on time |
| 标准 | biāozhǔn | standard | 数据标准 / Data standard |
| 质量 | zhìliàng | quality | 数据质量 / Data quality |
| 重点 | zhòngdiǎn | key point; priority | 本次会议的重点 / Meeting priority |
| 总结 | zǒngjié | summarize; summary | 每周总结 / Weekly summary |

Domain labels such as ERP, finance, inventory, role, and cutover may sit outside a learner’s HSK vocabulary. Introduce each label with a stable bilingual glossary entry rather than replacing a precise system term with an approximate translation. Example instruction: ‘请先检查库存数量，再确认订单。’ (Please check the inventory quantity first, then confirm the order.) Provide the English line immediately beside it and verify understanding by asking the user to demonstrate the steps.

Cadence: a weekly bilingual status note (progress, next tasks, risks, decisions needed); weekly process workshops with a glossary; role-based training before each test cycle; and a cutover notice with numbered steps, contact names, and escalation options. HSK vocabulary labels in this report follow the HSK 3.0 reference list; the Chinese Test Service has announced worldwide launch on 13 December 2026, so the learner’s target syllabus should be checked against their exam registration. [3][4]

# 8. Reflection

Planning makes dependencies visible before they become launch problems. For example, a production plan depends on trustworthy product records, usable inventory, purchasing lead times, and clear approval roles. If these are left until late testing, the team may discover that a process is technically configured but operationally unusable. A phase plan with named owners, test evidence, and decision gates makes readiness discussable rather than assumed.

Language accessibility is part of control design. If users misunderstand a field label, approval request, or cutover step, the result can be a wrong entry or missed task even when the software works as designed. HSK 4 vocabulary can make routine updates more accessible, while bilingual technical glossaries and teach-back protect precision for domain terms. The project should measure comprehension through task completion and questions raised, not by counting translated pages. This plan is a learning blueprint; it is not evidence of a live implementation or completed system configuration.

# References

[1] SAP, SAP Activate Methodology overview: https://www.sap.com/products/erp/activate-methodology.html

[2] SAP Learning, Describing the Methodology Structure: https://learning.sap.com/courses/discovering-sap-activate-implementation-tools-and-methodology/describing-the-methodology-structure_d959f6fc-ebfc-4143-94b3-6b83a6339b8b

[3] Chinese Test Service, announcement of worldwide HSK 3.0 launch on 13 December 2026: https://old.chinesetest.cn/gonewcontent.do?flag=kdnew&id=51336883

[4] WordSwing HSK, HSK 4 word list (2025 HSK 3.0 syllabus; consulted for the vocabulary examples): https://hsk.wordswing.com/vocabulary/hsk-4/